## Slide 1: 500 final-year engineers, 7 days, ₹2,000
NXTWAVE GROWTH CHALLENGE · ROUND 1
WHO
Final-year B.Tech students at tier-2 and tier-3 colleges, close to placement season with no AI project to show.
WHY THEY CARE
Recruiters now ask what you have built with AI. Most students have only theory.
WHY THEY REGISTER
Free, 60 minutes, no AI experience needed, a certificate, and a link their class group will forward.
Targets in this plan are planning assumptions, not measured results · 1 / 5

## Slide 2: Referrals beat paid ads at ₹2,000
PAID ADS (ASSUMED ₹10–15 PER CLICK)
About 130–200 clicks. At a 25% sign-up rate that is roughly 35–50 registrations, far short of 500.
PEER REFERRALS ON WHATSAPP
Students already trust their class groups. Every registrant gets a personal link to forward, so each sign-up can bring in more.
1
Register
2
Get a personal link
3
Share to class group
4
Friends register, repeat
Goal: each of 50–80 seed students brings in more than one friend (K above 1, to be tested) · 2 / 5

## Slide 3: Three channels, in priority order
CHANNEL | WHAT I DO | TARGET | BUDGET
P0 · WhatsApp groups | Brief 30 club leads and class reps with a forward-ready message | 350 | ₹500
P1 · LinkedIn organic | Placement reality-check posts and club DMs | 90 | ₹0
P2 · Instagram Reels | Two short hooks, boosted | 70 | ₹1,500
Total |  | 510 | ₹2,000
WhatsApp budget covers small digital rewards only. Channel targets are assumptions to validate in week 1 · 3 / 5

## Slide 4: 7-day plan with daily targets
DAYS 1–2
Seed
Brief ambassadors, launch in class groups.
Target: 80
DAYS 3–4
Social proof
Share live count, leaderboard, LinkedIn posts.
Target: 250
DAYS 5–6
Urgency
Seat-cap messages, boosted Reels, referral rewards.
Target: 430
DAY 7
Final push
12-hour reminder to every group.
Target: 500+
Cumulative registrations are targets · 4 / 5

## Slide 5: Built: a referral engine, not just a landing page
WHAT IT DOES
Sign-up with six fields, instant personal link, one-tap WhatsApp share, live leaderboard, CSV export for follow-up.
Live link: [add deployed URL]
AI IDEAS I REJECTED
Four paid channels: clicks cost too much. A RAG chatbot: it answers questions, it doesn’t drive sign-ups. ID-card upload: too much drop-off on mobile.
WITH 24 MORE HOURS
Live WhatsApp and email automation, a college-vs-college leaderboard, and a 3-day reminder drip to lift attendance.
5 / 5